## Sheet1
Appendix-6
Details of the Schemes whose Expenditure is funded under Special Allowance
Name of the Station: Rihand STPS Stage-I
Sl. No. | Name of Scheme** (including completed schemes) | Actual / Estimated/ Awarded Value | Exp. Upto 31.03.2018 Rs. Cr.) | Proposed Expenditure (Rs. Cr) |  |  | Remarks/ Status $$
|  |  |  | 2018-19 | 2019-20 | 2020-21
1 | Replacement of IP Turbine keep rings, assembly of emergency trip valve gear and assembly of emergency trip gear | 2.69 | 0 | 2.69 | 0 | 0 | Awarded
2 | Replacement of Economiser bank coils in Unit-1&2 | 8.7 | 0 | 8.7 | 0 | 0 | Awarded
3 | Replacement of Mill APH 25 VAL1300 of stage-I (2 x 500 MW | 13.57 | 0 | 13.57 | 0 | 0 | Awarded
4 | Replacement of existing volumetric feeder of Stage-1 with Gravimetric Coal Feeder at NTPC Rihand | 8.88 | 0 | 0.88 | 8 | 0 | Awarded
5 | Replacement of Fire detection & protection System (Smoke detectors with control panels) & Fire Proof cables | 1.14 | 0 | 0.8 | 0.34 | 0 | Awarded
6 | Replacement of 3.3 KV Unit Switch Gear | 11.08 | 0 | 10.8 | 0.28 | 0 | Awarded
7 | Procurement of Spare Generator Rotor for Stage-I | 49.13 | 49.13 | 0 | 0 | 0 | Implemented
8 | Replacement of HVAC System for Stage-1 (Screw Chillers for Main Plant St-1, CCR area, CHP , CWPH, Hydrogen Plant & S/Y.) | 3.76 | 0 | 2.63 | 1.13 | 0 | Awarded
9 | Replacement of 03 Nos IAC & 02 nos SAC with indigenous Screw Compressors & Control Panels having PLC based logic systems. 1. oil free screw air compressor- ZR 355, Qty- 05 Nos. 2. Air Dryer Md1000 For Zr 355- 3 nos. | 9.24 | 0 | 6.47 | 2.77 | 0 | Awarded
10 | Replacement of Fixed Spray Engines with Pumps with indigenous pumps and other accesssories in ST-1 (03 nos.) | 1.37 | 0 | 1.37 | 0 | 0 | Awarded
11 | Replacement of ACW Pumps, Band Screen Wash water pumps and ACW strainers with indigenous models | 0.94 | 0 | 0.94 | 0 | 0 | Awarded
12 | Replacement of various vertical in line pumps with motors in DM Plant of ST-1 with indigenous make. | 3.47 | 0 | 3.47 | 0 | 0 | Awarded
13 | Replacement of Foam bladder tanks for Fire Protection with accessories in HFO Tanks ST-1 with indigenous make | 2.19 | 0 | 2.19 | 0 | 0 | To be awarded
14 | Replacement of Fire Booster Engine with indigenous make Pump in ST-1 | 0.16 | 0 | 0 | 0.16 | 0 | To be awarded
15 | Replacement of all deluge valves in ST-1 by indigenous one. (24 nos.) | 0.22 | 0.22 | 0 | 0 | 0 | Completed
16 | Replacement of 01 No old Dozers | 2.47 | 2.47 | 0 | 0 | 0 | Completed
17 | Replacement of hydra 12 ton capacity-01 No | 0.1 | 0 | 0.1 | 0 | 0 | Awarded
18 | Replacement of 04 nos. old Turbo Super Chargers of Stage-I WDM2 locos with New ABB Turbo Super Chargers | 1.29 | 1.29 | 0 | 0 | 0 | Completed
19 | Replacement of 'Wheel and Axle Assly' of Stage-I BOBR wagons with new one | 9 | 0 | 3 | 6 | 0 | 9
20 | Replacement of Door assembly (Inner/Outer) for Stage-I Cimmco wagons | 0.77 | 0 | 0.77 | 0 | 0
21 | NAS VALUE ANALYSER | 0.17 | 0.17 | 0 | 0 | 0 | Completed
22 | PH ANALYSER COMPLETE | 0.04 | 0.04 | 0 | 0 | 0 | Completed
23 | ACID TITRATOR:COMP ASSY | 0.04 | 0.04 | 0 | 0 | 0 | Completed
24 | DISSOLVED OXYGEN ANALYSER | 0.07 | 0 | 0.07 | 0 | 0
25 | DEW POINT METER FOR MOISTURE | 0.35 | 0 | 0.35 | 0 | 0
26 | JAW-CRUSHER:COMP ASSY | 0.11 | 0 | 0.11 | 0 | 0
27 | GAS CHROMATOGRAPH:COMP ASSY | 0.34 | 0 | 0.34 | 0 | 0
28 | SIEVE SHAKER - COMPLETE ASSY. | 0.09 | 0.09 | 0 | 0 | 0 | Completed
29 | FURNACE(VM) | 0.15 | 0 | 0.15 | 0 | 0
30 | OVEN (MEDIUM) | 0.1 | 0 | 0.1 | 0 | 0
31 | COAL PULVERISER COMPLETE ASEMBLY | 0.03 | 0 | 0.03 | 0 | 0
32 | CONDUCTIVITY METER COMPLTE ASSEMBLY | 0.09 | 0 | 0.09 | 0 | 0
33 | TURBIDITY METER | 0.06 | 0 | 0.06 | 0 | 0
34 | ULTRA PURE WATER COMPLETE ASSEMBLY | 0.07 | 0 | 0.07 | 0 | 0
35 | AUTIOMATIC BOMB CALORIMETER | 0.18 | 0 | 0.18 | 0 | 0
36 | ATOMIC ABSORPTION SPECTROPHOTOMETER | 0.31 | 0 | 0.31 | 0 | 0
37 | SPECTROPHOTOMETER | 0.16 | 0.16 | 0 | 0 | 0 | Completed
38 | STACK MONITORING KIT | 0.03 | 0 | 0.03 | 0 | 0
39 | RDS | 0.07 | 0.07 | 0 | 0 | 0 | Completed
40 | FLUE GAS ANALYSER | 0.11 | 0.11 | 0 | 0 | 0 | Completed
41 | TOC ANALYSER | 0.22 | 0 | 0.22 | 0 | 0
42 | COAL PULVERISER | 0.02 | 0 | 0.02 | 0 | 0
43 | JCB PAY LOADER with Back Hoe | 0.22 | 0.22 | 0 | 0 | 0
44 | Hydra crane CAP 12 MT | 0.1 | 0 | 0.1 | 0 | 0
45 | Portable alloy analyser | 0.33 | 0 | 0.33 | 0 | 0
46 | Stress releaving machine | 0.05 | 0.05 | 0 | 0 | 0
47 | Hydraulic Jack 100MT | 0.05 | 0 | 0.05 | 0 | 0
48 | TC: Fork Lift 5 Ton | 0.12 | 0 | 0.12 | 0 | 0
49 | Battery operated Tow truck- 10T*** (Battery operated Trolly) | 0.05 | 0 | 0.05 | 0 | 0
50 | 4 Sheave Pulley Block : 10T | 0.05 | 0 | 0.05 | 0 | 0
51 | Walkie Talkie with charger | 0.01 | 0 | 0.01 | 0 | 0
52 | Intel server, Dual CPU, Quad Core, Xeon | 0.03 | 0 | 0.03 | 0 | 0
53 | Digital portable level meter for PLCC | 0.19 | 0.1 | 0.09 | 0 | 0
54 | B.G. push trolly complete with axle ** |  | 0 | 0 | 0 | 0
55 | DIP Lorry for material shifting in MGR ** |  |  | 0 | 0 | 0
56 | Vibration analyser with Cond. Moniter S/W | 0.21 | 0 | 0.21 | 0 | 0
57 | Power Hyd: Jack 200T- 150MM:COMPL:JACK | 0.05 | 0.05 | 0 | 0 | 0
58 | ESP (Already covered in Phase-I R&M-Scheme No.: A2) | 120.33 | 116.33 | 4 | 0 | 0
59 | 1st Raising of Mithini ash dyke lagoon-I | 7.23 | 7.06 | 0.17 | 0 | 0
60 | 1std Raising of Central ash dyke-I | 1.08 | 1.08 | 0 | 0 | 0
61 | 1std Raising of Central ash dyke-II | 8.94 | 8.74 | 0.2 | 0 | 0
62 | 2nd Raising of Central ash dyke- I | 5.94 | 5.74 | 0.2 | 0 | 0
63 | Ist Raising of Mithini Ash Dyke Lagoon-II | 10.86 | 10.17 | 0.69 | 0 | 0
64 | 1st Raising of Mithini ash dyke lagoon-I | 1.96 | 1.88 | 0.08 | 0 | 0
65 | 2nd Raising of Central ash dyke-II | 8.6 | 8.5 | 0.1 | 0 | 0
66 | 1st Raising of Mithini ash dyke lagoon-II (Hill side) | 6.86 | 5.45 | 1.41 | 0 | 0
67 | 3rd raising of Central Ash dyke lagoon -1 | 7.44 | 3.96 | 3.23 | 0.25 | 0
68 | 2nd raising of Mithini ash dyke lagoon -1 | 11.96 | 4.66 | 5 | 2.3 | 0
69 | Procurement of complete stator water skid with alkalyser for stage-1 generators | 19 | 0 | 14 | 5 | 0
| Total | 344.64 | 227.78 | 90.63 | 26.23 | 0

## Sheet2 (hidden)
R&M
| Installation of Coal Bunker Gates (Rod type cut off Gates) for Coal feeders Qty=16 Nos | 1.53 | 1.53 | 0 | 0 | 0 | Implemented
| Replacement of existing 3.3KV CHP switchgear with indigenous switchgear | 1.87 | 1.87 | 0 | 0 | 0 | Implemented
| Renovation of breakers in 400KV & 132 KV switch yard.(06 Nos Breakers each) | 2.76 | 2.76 | 0 | 0 | 0 | Implemented
| Renovation of Auto turbine run-up system and Governing system | 20.35 | 20.35 | 0 | 0 | 0 | Implemented
| Renovation of DAS along with the control system of both units. | 11.28 | 11.28 | 0 | 0 | 0 | Implemented
| Turbine Bearing vibration monitoring system U# 1&2 | 1.84 | 1.84 | 0 | 0 | 0
| Vibration monitoring system of BFP,CEP, ID & PA Fans of U#2 | 0.58 | 0.58 | 0 | 0 | 0
| BMS, Mill, Feeder, MFT system for unit #1 & 2(FSSS) | 11.64 | 11.64 | 0 | 0 | 0
| E25- Ash slurry pump house control system- PLC based system. | 0.7 | 0.7 | 0 | 0 | 0
| Provision of 08 No higher capacity flap valves actuator in crusher house | 0.006 | 0.006 | 0 | 0 | 0
Mid life R&M
| Replacement of 3.3 KV Ash and dust plant switchgear of stage- 1 | 2.36 | 2.36 | 0 | 0 | 0
| Renovation of existing electro mechanical GRP Relays of Stage – I by numerical relays | 1.13 | 1.13 | 0 | 0 | 0
| Replacement of PA system ( Main plant + CHP) of stage-1 | 0.61 | 0.61 | 0 | 0 | 0
| Renovation of existing DTH Relays of Stage – I & 2 by numerical relays | 0.43 | 0.43 | 0 | 0 | 0
| Replacement of 12 NOs 400 KV line side CVT of stage-1. | 0.37 | 0.37 | 0 | 0 | 0
| Installation of PLC in place of existing electric relay logic & electronic card control for Stacker-reclaimer of CHP St-1. | 0.23 | 0.23 | 0 | 0 | 0
| Procurement of CI Wafer Type Butter Fly Valves for DM Plant St- 1. | 0.22 | 0.22 | 0 | 0 | 0
| Procurement of Centre line (RS) Wafer Type Soft seated Butter Fly Valves for DM Plant St- 1. | 0.005 | 0.005 | 0 | 0 | 0
| Procurement of Weir BDK Make Butter Fly Valves (Model-12) for DM Plant St- 1. | 0.06 | 0.06 | 0 | 0 | 0
| R&M / replacement of 4 Nos. Plate Type Heat Exchangers of St 1 Stator Water System. | 0.32 | 0.32 | 0 | 0 | 0
| R&M / Replacement of 12 NOs Lube oil Pumps of ID Fans Stage-1. | 0.24 | 0.24 | 0 | 0 | 0
| R&M of Turbine HP/LP BYPASS CONTROL System (Relay Based) Stage-1 to DCS based Turbine including HP / MP Relief V/Vs (ERV’s). | 2.49 | 2.49 | 0 | 0 | 0
| R&M of TG AUXULIARIES CONTROL System to DCS based TG AUX CONTROL SYSTEM Stage-I | 3.31 | 3.31 | 0 | 0 | 0
| Retrofitting and replacement of all the 4 (four) nos. of Trash Screens at stg.-1 Crusher house of CHP | 2.86 | 2.86 | 0 | 0 | 0
| Supply, Installation and Commissioning of Air Washer System in ADPH Stage - I | 0.13 | 0.13 | 0 | 0 | 0
Mega R&M