## Kahalgaon STPS-I
Annexure-V (C)
Name of Generating Station : Kahalgaon STPS Stage-I (840 MW)
Stage: I
COD of Units/Station : 01.08.1996
Details of expenditure incurred from Compensation Allowance and Special Allowance during Tariff Period 2009-14
FY Year | Add-cap allowed by the Commission under the provision of Regulation 9(2) |  | Compensatory allowance allowed by the Commission, if any | Special allowance allowed by the Commission, if any | Details of Asset/Work wise Capitalisation based on the Expenditure allowed by the Commission in the tariff period 2009-14 | [5 empty] | Capitalisation done which has not been claimed/ allowed in the tariff | Difference of Allowed vs Expenditure | Capital Spares | Total Addition during the year | Total Addition during the year as per duly audited Schedule of Fixed Asset | Variation if any to be reconciled /justified.
[5 empty] | Capitalisation out of add cap allowed under Regulation 9(2) |  | Capitalisation out of Compensation allowance in the stations wherever applicable |  | Capitalisation out of Special Allowance allowed in the stations where applicable
| Net Basis | Liability of (2) |  |  | Asset/work | Rs(Lakh) | Asset/work | Rs(Lakh)- Gross | Asset/work | (Rs. lakh)
1 | 2 | 3 | 4 | 5 | 6 |  | 7 |  | 8 |  | 9 | 10=(2+3+4+5)-(6+7+8+9) | 11 | 12=6+7+8+9+11 | 13 | 14
2009-10 | 301.78 | 11.5851 | 126 | 0 | Ash Handling System | 207.2423 |  |  |  |  | 0 | 125.9961 | 0 | 313.3691 | -577.5486 | Decap of construction equipment (-445.89), Decap of Vehicle (-16.08), Decap of MBOA (-3.57),Deacp of spares (-243.50), Deacp of Wagon (-171.83), ERV (-10.06)
[5 empty] | AAQMS | 104.043 |  | -
[5 empty] | Land Compensation | 2.0838
[5 empty] | Total | 313.3691 | Total | 0 | Total | 0 |  |  |  | 313.3691 | -577.5486
2010-11 | 867.07 | 21.0569 | 210 | 0 | Ash Handling System | 888.1305 |  | - |  |  | 0 | 209.9963 | 641.7 | 1529.8306 | 658 | Decap of equipment (-6.75), Decap of MBOA (-14.87), Decap of spares (-123.40), ERV (1.96), Inter unit Transfer (-5.48), Asset not owned by company (-99.83), Decap of wagon (-619.02), Liability reversal (-4.42)
[5 empty] | Total | 888.1305 | Total | 0 | Total | 0 |  |  |  | 1529.8306 | 658
2011-12 | 7837.6 | 1152.2609 | 252 | 0 | Ash Handling System | 30.6935 |  |  |  |  | 56.8993 | 195.1017 | 321.2413 | 9368.0005 | 8911.3978 | Decap of spares (-176.34), ERV (6.38), Inter Unit Transfer (975.42), Decap of wagons (-240.1), Locomotive no. 3 (-1021.96) Capitalised during 2012-13 in books after returned from Rihand, But claimed in 2011-12
[5 empty] | Wagon Tippler | 5855.8354
[5 empty] | Locomotive (3 Nos. | 3065.4198
[5 empty] | Land Compensation | 37.9113
[5 empty] | Total | 8989.86 | Total | 0 | Total | 0 |  |  |  | 9368.0005 | 8911.3978
2012-13 | 2979.4356 | 314.4739 | 294 | 0 | Ash handling System | 1580.8781 |  |  |  |  | 0 | 294 | 886.2765 | 4180.186 | 3125.09 | Decap Spares-Part of Capital cost (-116.53),Wagon-decap (-44.34),Deacap of spares-not part of Capital cost(-1.099),Liabilty reversal (-6.98), Loan ERV (2.58), Iner Unit Transfer (-888.73),
[5 empty] | Wagon Tippler Package | 1425.3642
[5 empty] | Land Compensation | 287.6673
[5 empty] | Total | 3293.9095 | Total | 0 | Total | 0 |  |  |  | 4180.186 | 3125.09
2013-14 | 717.11 | 9.9403 | 294 | 0 | Ash handling System | 218.2931 | Bunker Level Monitoring System | 66.909 |  |  | 0 | 165.3902 | 647.2582 | 1502.9183 | 4209.89 | Decap Spares-Part of Capital cost (-267.68), Decap of spares-not part of capital cost (-55.34), Decap of MBOA (-1.156), Liability Reversal (-96.793), Revenue item decap (-8.04), ERV (1.18456); 5 KM Scheme allowed as reimbursement (Not Capitalised) : Rs3134.79 Lakhs
[5 empty] | Augmentation of Railway siding | 437.7274 | Ash Utilization (Brick Making Machine) | 61.7045
[5 empty] | Land Compensation | 71.026
[5 empty] | Total | 727.0466 | Total | 128.6135 | Total | 0 |  |  |  | 1502.9183 | 4209.89
Details of expenditure incurred from Compensation Allowance and Special Allowance during Tariff Period 2014-17
FY Year | Add-cap allowed by the Commission under the provision of Regulation 14(3) |  | Compensatory allowance allowed by the Commission, if any | Special allowance allowed by the Commission, if any | Details of Asset/Work wise Capitalisation based on the Expenditure allowed by the Commission in the tariff period 2009-14 | [5 empty] | Capitalisation done which has not been claimed/ allowed in the tariff | Difference of Allowed vs Expenditure | Capital Spares | Total Addition during the year | Total Addition during the year as per duly audited Schedule of Fixed Asset | Variation if any to be reconciled /justified.
[5 empty] | Capitalisation out of add cap allowed under Regulation 14 (2) |  | Capitalisation out of Compensation allowance in the stations wherever applicable |  | Capitalisation out of Special Allowance allowed in the stations where applicable
| Net Basis | Liability of (2) |  |  | Asset/work | Rs(Lakh) | Asset/work | Rs(Lakh)- Gross | Asset/work | (Rs. lakh)
1 | 2 | 3 | 4 | 5 | 6=1+2 |  | 7 |  | 8 |  | 9 | 10=(2+3+4+5)-(6+7+8+9) | 11 | 12=6+7+8+9+11 | 13 | 14
2014-15 | 1500 |  | 420 | 0 | Land Compensation (New Item) | 1090.6807 | Wagons (10 No.) | 454.4928 |  |  | 0 | 150.1189 | 1331.748 | 3101.6291 | 2671.98 | Decap of Spares (-326.51), Reversal of Liabilty (-103.14),
[7 empty] | 132 KV Copper Conductor | 224.7077
[5 empty] | Total | 1090.6807 | Total | 679.2005 | Total | 0 |  |  |  | 3101.6291 | 2671.98
2015-16 | 690 |  | 630 | 0 | Ash Dyke (Allowed in 2014-15) | 1569.69 | Turbo supervisory/ turbine vibration monitoring system | 415.8174 |  |  | 0 | -1349.3886 | 1037.0707 | 3706.4593 | 98.1278 | Decap of Spares (-390.53), Decap of MBOA (-24.66), Decap of 5KM Scheme (-3036.94), Decap of Equipment (-156.20)
[5 empty] | Land Compensation ( New Item) | 339.7394 | Upgrade of exist relay control system make up pump | 89
[5 empty] | Continuous Emission Monitoring System ( New Item) | 255.1413
[5 empty] | Total | 2164.5712 | Total | 504.8174 | 0 | 0 |  |  |  | 3706.4593
2016-17 | 2804 |  | 735 | Nil
2016-17 | 2794 |  | 735 | 0 | Ash Dyke Work | 1498.75 | Envirornment, Energy Conservation, Energy Mgt. | 43.5356 |  |  | 0 | 4789.9603 | 2028.6 | 6527.6726 | 8582.431 | Wagon Damaged (-28.7), Decap of MBOA (-14.4), Decap of Spares (-454), Inter Unit ( 1102.93), Reversal of Liabilty (-45.86), Ind AS Adjustment (1495.78)
[5 empty] | Land Compensation | 120.3061 | OH/R&M | 2836.4808
[5 empty] | Total | 1619.0561 | Total | 2880.0165

## Sheet1
Annexure
For 2014-15
Sl. No. | Description | Allowed by CERC | Actua Capitalization | Justification/ Reason
1 | Ash Dyke work | 1500 | 0 | Spilled over to Next year
2 | Land Compensation | 0 | 1090.6807 | Detailed Justification in true up petition
| Total | 1500 | 1090.6807
For 2015-16
Sl. No. | Description | Allowed by CERC | Actua Capitalization | Justification/ Reason
1 | Replacement of Halon System with Inert gas | 230 | 0 | spilled over to Next year
2 | Fire Detection and Protection System | 460 | 0 | spilled over to Next year
3 | Ash Dyke Work | - | 1569.69 | Allowed in 2014-15
4 | Land Compensation | 0 | 339.7394 | CERC has allowed the same vide order dated pertain ing to…..
5 | Continuous Emission Monitoring System |  | 255.1413 | Installed for continious monitoring of emission parameters in view of Environment Norms
| Total | 690 | 2164.5707

## XVI A_VSTPS_V (hidden)
Annexure XVI A
Details of Incidental Expenses during Construction (IDEC) with break-up for the Generating stations for which COD is declared after 1.4.2014
Name of Generating Station : Vindhyachal STP Stage- V
Stage : Stage - V
COD of Units/Station : 30.10.2015
Rs-Lac
S. No. | Item-wise details of expenditure with break-up | Expenditure as on SCOD | Expenditure as on actual COD of unit/ station | Time Overrun
A | Head of Expenses: |  |  | No
1 | Const Power Chrgs | 5275.9295 | 5275.9295
2 | IEDC Allocated by CC (Capital) | 2913.1078 | 2913.1078
3 | Salaries | 2595.5164 | 2595.5164
4 | Contribution to PF | 379.653 | 379.653
5 | Employee Welfare Exp. | 112.2326 | 112.2326
6 | R&M - Bldg | 35.7926 | 35.7926
7 | R&M - Others | 163.4667 | 163.4667
8 | Rates & Taxes | 6.0843 | 6.0843
9 | Communication Exp | 14.1198 | 14.1198
10 | Bank Charges | 1.8814 | 1.8814
11 | Travel Expenses | 164.4169 | 164.4169
12 | Tender Expenses | 71.3213 | 71.3213
13 | Advertisement & Publicity | 2.0828 | 2.0828
14 | Security Exp | 72.2292 | 72.2292
15 | Entertainment Exp | 10.6657 | 10.6657
16 | Professional Charges | 4.7648 | 4.7648
17 | Legal Exp | 9.197 | 9.197
18 | Printing exp | 0.06006 | 0.06006
19 | Transport vehicle Running Exp | -3.5693 | -3.5693
20 | Misc Exp | 1836.7101 | 1836.7101
21 | Depreciation (Tangible Assets) | 264.7635 | 264.7635
22 | Depreciation (Intangible Assets) | 0 | 0
A | Total Expenses | 13930.4262 | 13930.4262
B | Head of Income | 0 | 0
1 | Misc Income | 28.2195 | 28.2195
2 | Power Charges Recovery | 40.2799 | 40.2799
3 | Interest from Contractors | 117.5189 | 117.5189
4 | Water Charges Recovery | 0.00327 | 0.00327
5 | Hire Charges Recovery | 0.47368 | 0.47368
B | TOTAL INCOME | 186.4953 | 186.4953
|  | 0 | 0
A-B | NET TOTAL | 13743.9309 | 13743.9309
| Capitalised on COD | 12492.96 | 12492.96
| Balance in CWIP on COD | 1250.9709 | 1250.9709