## Sheet2
Appendix-1
Details of the Schemes whose Expenditure is funded under Special Allowance
Name of the Station: Singrauli Super Thermal Station (2000 MW)
Sl. No. | Name of Scheme (including completed schemes) | Awarded/ Estimated/ Completed Value (Rs. Cr.) | Exp. Upto 31.03.2018 Rs. Cr.) | Proposed Expenditure (Rs. Cr) |  |  | Remarks/ Status
|  |  |  | 2018-19 | 2019-20 | 2020-21
1 | R&M of C&I of Main Plant (Boiler and station control) and Off site areas.(For Unit # 4 & 5 station C&I Control excluded) | 57 | 28 | 19 | 10
2 | Renovation & retrofitting of microprocessor based conversion kit control in gravimetric feeders in 2 units.( Stage-I) | 5.72 | nil | 5.72
3 | Bunker level measurement | 1.19 | nil | 1.19
4 | Replacement of DM plant field Instruments | 3.39 | nil |  |  | 3.39 | Planned
5 | Replacement of CCTV system for plant. | 2.57 | nil | 2.57
6 | Replacement of ERV | 0.72 | nil | 0.72
7 | Replacement of Gravimetric feeder control system (stage-II) | 8.72 | nil | 8.72
8 | Replacement of flame scanner assemblies | 2.66 | nil | 2.66
9 | Replacement of Steam water analysis system | 3.77 | nil | 3.77
..
10 | Replacement of Bottom ash gate hydraulic system (St-I) | 6.15 |  |  | 6.15 |  | Tendor Document vetted on 6/2/18
11 | Renovation of pipe lines of Ash disposal pipe lines (10 km) | 10 |  |  |  | 10 | QR to be finalized by NRHQ
12 | Renovation of pipe lines of Ash disposal pipe lines (qty. revised from 10 km to 56 km) | 34 |  |  |  | 34
13 | Replacement of BAH Gates & Renovation of its hydraulic operating system (St-II) | 6.08 |  |  | 6.08
14 | Renovation of HP, LP & Service water lines | 5.17 |  |  | 5.17
15 | Replacement of existing Submerged Scrapper Conveyors (SSC) (08 nos.) including drives | 13.303 |  |  |  | 13.303
16 | Replacement of critical piping, bends and Tees in MS, HRH & CRH lines ( RLA study of Critical Piping ). (Clubbed schemesA10, B4 of Stg-I). | 9.41 | 7.56 | 1.65 |  |  | Supply and service work has been completed in all units. 03 units final Reports out of 05 units is awaited.
17 | Replacement / Renovation of BFP. (Supply of Cartridge, Hydraulic coupling awarded. Supervision work & Booster pump supply under award) | 4.39 | 4.39 |  |  |  | 1 GBP=90.44 INR
|  | 26.22 |  | 26.22
|  | 29.99 |  |  |  | 29.99
18 | HP/ IP nozzles, CV servomotors, ESV + servo motors, HP control valve, IP control valve, IV+servomotors | 10.17 | Nil | 10.17 |  |  | PR initiated . PO yet to be awarded.
19 | Replacement of high-energy drains valves. | 4 | Nil | 4 |  |  | PR initiated . PO yet to be awarded.
20 | Replacement of High Pressure Heaters. (For two units only). | 19.24 | -- | -- | 19.24 | -- | --
21 | Replacement of control valves seat of 500 MW Turbo-Generator | 1.92 |  | 1.92 |  |  | PR initiated . PO yet to be awarded.
22 | Replacement of 06 nos. CEP indigenous make pump sets along with motor and 2 nos cartridges | 14.82 |  | 14.82 |  |  | PR initiated . PO yet to be awarded.
23 | Replacement of high Energy drain Valves | 3.57 |  |  | 3.57 |  | PR initiated . PO yet to be awarded.
24 | Replacement of HP bypass valves with upgraded materials including C&I items | 14.47 |  |  | 14.47 |  | PR initiated . PO yet to be awarded.
25 | Replacement of APRDS valves | 1.53 |  |  | 1.53 |  | PR initiated . PO yet to be awarded.
26 | Replacement of 01 No Vacuum Pump | 1.3 |  |  | 1.3 |  | PR initiated . PO yet to be awarded.
27 | B1. Replacement of existing Economizer bank for one unit. (Awarded). | 3.32 | 2.57 | 0.75 |  |  | Material Recived at site installed in unit no-1,2,3 and 4.
28 | B3. Replacement of hanger & supports. | 9.24 |  |  |  | 9.24 | RLA Study Completed. Result awaited
30 | B10. Replacement of metallic expansion joints of flue gas, sec. air & pri. Air ducts (Awarded). | 6.81 |  | 6.8077
31 | B1. Replacement of the insulation & cladding of critical areas of boiler (condition based). | 9.82 |  | 2 | 7.82
32 | B2. Repair of duct (condition based) and replacement of all expansion joints & guide vanes from AHP outer to ESP | 12.69 |  |  | 12.69 |  | Not required as it has been covered in ESP R&M
33 | B3. Replacement of Super heater and Re-heater spray station valves | 6.05 |  |  | 6.05 |  | RH PR 300022624 dt 24.02.2016 in C&M.
34 | Replacement of complete assembly of CW pump – 01 set | 12.07 |  |  | 12.07 |  | Budgetary offer awaited fron M/s Hitachi .PR to be raised & processed.
35 | Replacement of two complete set of Lub water pumps | 0.12 |  | 0.12 |  |  | With C&M .Yet to be awarded.
36 | Replacement of complete one set of screen washer pump (01 set) | 1.09 |  | 1.09 |  |  | With C&M .Yet to be awarded.
37 | Replacement of Baskets of Travelling Water Screen | 7.52 |  |  | 7.52 |  | Budgetary offer awaited fron M/s Hitachi .PR to be raised & processed.
38 | Replacement of CW discharge valve operating unit (01 set) | 3.1 |  |  | 3.1 |  | Budgetary offer awaited fron M/s Hitachi .PR to be raised & processed.
39 | Replacement of MSRL pipes | 6.9 |  |  | 6.9 |  | Budgetary offer awaited.PR to be raised & processed
40 | Replacement of tanks & vessels of DM plant for both streams | 27.61 |  |  | 27.61 |  | Budgetary offer awaited.PR to be raised & processed
41 | Renovation of AC plant | 11.98 |  |  | 11.98 |  | Budgetary offer awaited.PR to be raised & processed
42 | Replacement of pneumatic operated Valves | 0.86 |  |  | 0.86 |  | Budgetary offer awaited.PR to be raised & processed
43 | Replacement of Regeneration system of CPU | 10.47 |  |  | 10.47 |  | Budgetary offer awaited.PR to be raised & processed
44 | Renovation of Fire Detection and Protection System at Unit # 6&7 Stage-II (2X500 MW) | 15.13 |  | 15.13
45 | Replacement of 132 kV Pneumatic operated isolators in 132 kV switchyard. | 1.83 |  |  | 1.83 |  | Under recommendation with TC member
46 | Replacement of 400 kV Pneumatic operated isolators in 400 kV switchyard. | 11.36 |  |  | 9.16 | 2.2 | Bid to be called
47 | Replacement of 132 kV MOCB in 132 kV switchyard. (Awarded) (Clubbed schemes D3, D4, D5 of stg-I). | 9.57 |  |  | 9.57 |  | TS Done . Price bid to be opened
48 | Replacement of 132 kV ABCB in 132 kV switchyard. (Clubbed schemes D3, D4, D5 of stg-I). | 0.4 |  |  |  | 0.4 | TS Done . Price bid to be opened
49 | Replacement of 400 kV ABCB in 400 kV switchyard. (Clubbed schemes D3, D4, D5 of stg-I). | 2.9 |  |  |  | 2.9 | TS Done . Price bid to be opened
50 | Renovation of PLCC panels. (Awarded) | 0.41 | 0.218 |  | 0.19 |  | Completed
51 | Renovation of GRP having numerical relay with DR/Event logger. (Awarded) | 7.69 |  |  | 7.69 |  | Clubbed with SAS
52 | Provision for Lighting mast in Switchyard and CHP area. (Awarded) | 1.87 | 1.21 | 0.66 |  |  | Erection work pending
53 | Complete renovation of CHP & Main Plant area (stage-I) lighting system. | 0.81 | 0.812 |  |  |  | PR no. 300026034 Under F&A vetting
54 | Replacement of MCCs including PLC based control for CHP & Stacker/ Reclaimers. | 5.43 |  |  | 5.43 |  | Under QR approval
55 | Replacement of HT and LT power cables (HT cable awarded) | 23.9 | 5.19 | 4 | 10 | 4.54 | Price bid to be opened
56 | Replacement of 31.5 MVA STs with new STs – 1 no. (Awarded). (Clubbed schemes D13, D14, D15 of stg-I). | 30.24 | 11.24 | 7 | 12
57 | Replacement of 12/16 MVA UATs with new UATs – 2 nos. (Awarded). (Clubbed schemes D13, D14, D15 of stg-I).
58 | Replacement of GT with new 250 MVA GT -3Nos. (Awarded). (Clubbed schemes D13, D14, D15 of stg-I).
59 | Renovation of 6.6 KV MOCB in Stage-I.Unit # 1, 2, 4 & 5, Station Switchgear Compressors switchgears, Aux. Pump house, Clarified Pump house, and CW pump house. (Awarded) | 14.12 |  |  | 7 | 7.12 | Price bid to be called
60 | Renovation of LIFTS of St-I | 1.85 |  | 0.5 | 1.35 |  | Award proposal to be initiated
61 | Replacement of 6.6 kV HT & LT old design motors. | 2.76 |  | 0.22 | 2.54 |  | F&A vetting pending
62 | Retrofitting of existing conventional schemes with Numerical Protection & Control and SAS including BB protection for 400 /132 kV switchyard SSTPS. (Awarded) | 16.23 | 15.64 | 0.6 |  |  | In progress
63 | Replacement of complete 6.6KV CW switchgear with relay & remote panel | 4.57 |  |  |  | 4.57 | Under bid invitation
64 | Provision of 1600 KVA, 6.9 / 0.4 KV Service transformers – 2 nos. (Awarded) (Clubbed schemes D21, D22 of stg-I). | 0.81 |  | 0.81 |  |  | under manufacturing
65 | Provision of 630 KVA, 6.9/0.4 KV Service transformers – 2 nos. (Awarded) (Clubbed schemes D21, D22 of stg-I). | 0.22 |  | 0.22 |  |  | under manufacturing
66 | Replacement of complete 6.6 KV Switchgear Boards of Main Plant and CHP of St-II . | 6.11 |  |  | 6.11 |  | Under bid creation
67 | Replacement of complete Stacker / Reclaimer-III 415 Volts MCC of CHP St-II. | 0.5 |  |  | 0.5 |  | Under bid creation
68 | Renovation of 260 KW IAC Motors based on health assessment - 02 no.s | 0.4 |  |  | 0.4 |  | Under TS
69 | Renovation of Mill motors (Procurement of 02 Nos. Vacuum pressure impregnatable energy efficient 525 KW, 6.6 KV motors) | 0.9 |  |  | 0.9 |  | Under TS
70 | Renovation of ARCW /DMCW 460/670 KW Motors with VPI Energy efficient motors - 1 no. each. | 1 |  |  | 1 |  | Under TS
71 | Replacement of BWC pumps assembly (02 No – CC pump motor with impeller). | 8.6 |  |  | 8.6 |  | Under negotiation for award
72 | Replacement of obsolete Battery Chargers of 220V & 24V system | 0.5 |  |  | 0.5 |  | Under release
73 | Renovation of Passenger/VIP Lifts (St-II & Admn. building). (02 nos) | 1 |  |  | 1 |  | Award proposal to be initiated
74 | Procurement of Dozers (6no) | 13.4 | 13.4 |  |  |  | Completed
75 | Inline Magnetic Separator (02 nos.) – 2A/B & 7A/B | 1.209 |  |  | 1.209 |  | Under PR release
76 | Suspended Magnet - (02 nos) – 7A/B & 9A/B | 1.453 |  |  | 1.453 |  | Under PR release
77 | DE /Dust Suppression system in crusher house of St.II | 0.605 |  |  | 0.605 |  | NIT to be published
78 | Life extension of Stacker /Reclaimer-III of Stage-II by replacing slew bearing & lubricating system. | 6.41 |  | 2.465 | 3.945 |  | 1. Slew brg replacement completed. 2. Procurement of gear boxes: Under price nogotiation
79 | Provision of Electronic belt Weigher in Conveyor-3A/B & 7A/B. (Awarded) | 0.27 |  | 0.27 |  |  | Completed
80 | Life extension of Stacker /Reclaimer-I & II of Stage-I. (Awarded) | 1.22 | 1.216 |  |  |  | Completed. (Rest out of 4.977 is already utilised in 2015-16)
81 | Provision of Fogging type dust separation system in crusher house of St.I including foam system HFO Day Tank | 0.99 |  |  | 0.991 |  | NIT to be published
82 | Procurement of 02 nos. WDG3 | 31.03 |  |  | 31.03 |  | BI under prepration
83 | Procurement of 40 nos. BOBR Wagons | 24.96 |  |  | 14.96 | 10 | File is under QR preparation
84 | Modification of Singrauli Track lay out | 36.99 |  |  |  | 36.99 | Budgetary offer has to be taken from M/S RITES. Proposal under prepration.
85 | Procurement of 180 Wheel Sets. | 4.93 |  | 2.43 | 2.5 |  | PO has been issued to M/S SAIL durgapur for 250 nos of wheel disc.Del Dt.18 month from PO place
86 | Procurement of complete one set of rerailing equipment | 0.56 | 0.56 |  |  |  | Material Has been received at MGR workshop FY(2016-17
87 | Phasing out S & T System at MGR Workshop and Jayant. | 32.79 |  |  | 6 | 26.79 | This scheam is in Year 2019-2029. 2019-24= 11.00 Cr 2024-29= 21.79 Cr
88 | CW Duct Replacement Package for SSTPS Stage-I | 68.05 | 45.4001 | 22.6498
89 | Supply & Installation of Dry Fly Ash Extraction and Transportation System Package for SSTPS St.-II (2X500 MW) | 15.5 | 14.8303 | 0.66972
90 | Replacement of CGI Sheet with precoated galvanised iron sheet of penthouse of stage-1 of NTPC Singrauli. | 4.11 | 0.65715 |  |  | 3.4529
91 | Replacement of Asbestos Sheet with Precoated GI Sheet of Penthouse of Conveyor Galleries including Track Hopper | 3.33 | 2.4828 | 0.8493
92 | 1st Raising of S2 Dyke | 6.93 | 0.271 | 6.66
93 | 2nd raising of ash dyke S-1 Lagoon-1 | 11.03 | 11.0286 | 0
94 | Civil works for Starter Ash Dyke (S-2 Lagoon ) for Singrauli Super Thermal Power Station Stage-I ( 5 X 200 MW) | 29.28 | 29.2821 | 0 |  |  | Under arbitration proceedings
95 | Renovation of sewerage pumps | 0.96 |  |  | 0.25 | 0.71 | Proposal planned
96 | ESP R&M | 383.42 | 304.37 | 30 | 30 | 19.05
| Total | 1281.66 | 500.328 | 209.0315 | 353.293 | 218.6459