## Scheme Status
Appendix-7
Details of the Schemes whose Expenditure is funded under Special Allowance
Name of the Stations: Unchhar Stage- I
Sl. No. | Name of Scheme | Awarded/ Estimated/ Completed Value (Rs. Cr.) | Exp. Upto 31.03.2018 (Rs. Cr.) | Proposed Expenditure (Rs. Cr) |  |  | Remarks /status
|  |  |  | 2018-19 | 2019-20 | 2020-21
1 | Supply, Installation,Testing & commissioning of Fire Fighting System for Stacker Reclaimer I & II | 7.104 | 5.46 | 1.56 | 0.084 | 0 | Under Implementation
2 | ESP Augmentation | 74.8 | 69.4009 | 5.3982 |  |  | Under Implementation/ Majority work completed
3 | Online Monitoring of CO2 in Flue gas at stack (Continuous Emission Monitoring System - CEMS Pkg) Awarded value 86.63570 & USD 24,791 | 1.68 | 1.6803 | 0 |  |  | Supply Completed
4 | Renovation of fire fighting system (Inert Gas system ) | 1.702 | 1.7 | 0 |  |  | Scheme completed & contract closed
5 | RLA Study of Critical Piping and hangers | 3.005 | 1.0768 | 1.928 |  |  | Under Implementation
6 | Up-gradation of Off-Site Control & Instrumentation System of Stage-I. (2X210 MW) | 6.86 | 0 | 3.468 | 3 | 0.392 | Detail Engineering started.
7 | Replacement of LT MCC of Stage-I. (2X210 MW) Off-site | 7.34 | 0 | 0 | 4 | 3.34 | Price Bid opened on 09/02/2018 & cancelled due to high price variation / under-re-tendering
8 | Replacement of LP Heaters | 7.9 | 0 | 0 | 6.32 | 1.58 | Under Award
9 | Replacement of field devices Servo & Blocking Unit of HPBP system of Stage-I. (2X210 MW) | 2.145 | 1.9493 | 0.19528 |  | 0 | Under Implementation
10 | Replacement of Lifts of Stage-I. (2X210 MW) | 1.6 | 0 | 1.6 |  |  | Material (2 Nos lift) received at site.
11 | Replacement of CHP Traveling Trippers of Stage-I. (2X210 MW) | 1.974 | 0 | 0.74348 | 1.23 |  | PO placed
12 | Replacement of MAL Valves with actuators of Stage-I | 0.877 | 0 | 0.75 | 0.127 |  | PO. placed to BHEL.
13 | Replacement of BFP & CEP of Stage-I | 5.57 | 5.5695
14 | Replacement of Servomotor assembly of Turbine Critical Valves of Stage-I | 2.442 | 0.24416 | 1.25 | 0.947 |  | PO placed on 10/03/2018 to M/s BHEL
15 | Conversion of open Channel Ash water flow to Closed pipe corridor flow/ Construction of concrete pedestal for laying of 650 mm Dia MS pipe for bringing back ash water | 3.5 | 0 | 2.738 | 0.76 |  | PO placed to M/s SAIL/ Civil works awarded
16 | Replacement of DC chargers of Stage-I (Common ratings for all chargers) | 0.339 | 0 | 0.3 | 0.039 |  | PO placed
17 | Second Battery bank along with Chargers of Stage-I (Ni-Cad & plante) | 1.65 | 0 | 0.88937 | 0.76063 |  | Under tech scrutiny
18 | Supply of Control Cables | 3.33 | 0 | 2 | 1.33 |  | under approval
19 | Supply of Power Cables | 3.572 | 0 | 3 | 0.5724 |  | Under PBOD approval.
20 | 1.0-Replacement of 220 kV Isolators of Stage-I (2X210 MW) | 1.97 | 0 | 1 | 0.97 |  | Under QR preparation
| 2.0 Replacement of Bus Post Insulators of 245 Kv – 97 sets | 0.3 | 0 | 0.3
21 | Renovation of Paddle Feeders & Associated Concrete Structure of Stage-I. (2X210 MW) | 6.8 | 0 | 0.87369 | 3.963 | 1.963 | Under TS
22 | Replacement of Sleepers with PRC Sleepers in MGR System of Stage-I. (2X210 MW) | 34.2 | 0 | 17.6 | 16.6 |  | Under Award
| S&T system in MGR of Stage-I. (2X210 MW)in MGR of Stage-I | 16.51 | 0 |  | 10 | 6.51 | PR to be raised
23 | Renovation / Re-development of UPVNRN (Unchahar Township) | 6.57 | 0 | 3.35 | 2.78 | 0.44 | Under Various stages of NIT/ Award
24 | Refurbishment of Cooling Tower of Stage-I | 9.38 | 0 | 2.87 | 5 | 1.51 | BOD Extended
25 | Replacement of Cast Basalt Lined pipes of Stage-I. (2X210 MW) | 6.08 |  | 1 | 5.084
26 | R&M of Cladding Sheet of Conv. Galleries & MUTH of Stg-1 | 1.128 | 0 | 0.51793 | 0.61 |  | NIT to be issued.
| Total-C | 220.328 | 87.0809 | 53.3319 | 64.177 | 15.735